## Multi-Framework-Gap-Analysis
Gap ID | Process Area | Control / Requirement | Description | NIST CSF Ref | ISO/IEC 27001:2022 Ref | RBI Ref | Current Maturity (0-5) | Current State / Evidence | Gap Statement | Risk / Impact | Priority (P1-P4) | Compensating Controls (Current) | Remediation Plan (Actions) | Owner | Dependencies | Target Date | Status (Open/In Progress/Closed) | Validation / Evidence Required | Last Reviewed | Notes
GAP-001 | Asset Management | Asset inventory completeness | Asset inventory must support incident scoping (hosts/users/apps/cloud) | ID.AM-1 / ID.AM-2 | A.5.9 (Inventory of information and other associated assets) | II.1 | 2 | Partial CMDB export available; client asset registers inconsistent | No single reliable asset source; delays in incident scoping and containment | Delayed containment; incomplete impact assessment; audit findings | P2 | Manual enrichment using SIEM/EDR asset fields | Create authoritative asset inventory workflow; define required fields; monthly reconciliation with EDR & CMDB | IT Ops + SOC Manager | CMDB team, Client IT (MSSP) | YYYY-MM-DD | Open | Monthly asset reconciliation report; completeness score; audit evidence pack | YYYY-MM-DD | Define minimum fields: hostname, IP, owner, criticality, location, EDR status
GAP-002 | Endpoint Security | EDR coverage & health | EDR must be deployed and healthy on endpoints/servers for detection/containment | DE.CM-4 / PR.IP-1 | A.8.7 (Protection against malware) | III.6 | 3 | EDR coverage report shows 92–95% depending on segment | EDR gaps exist on critical servers and remote endpoints | Reduced visibility; missed detections; containment limitations | P1 | Network-based detections via SIEM; AV logs | Enforce EDR coverage KPI ≥98%; implement onboarding checklist; auto-alert on agent inactive >30 min | IT Ops + SOC Lead | Server owners, Change mgmt | YYYY-MM-DD | In Progress | EDR coverage dashboard; exception register entries for exclusions | YYYY-MM-DD | Track exceptions in Policy-Exception-Register
GAP-003 | Logging & Monitoring | Log source coverage | Log sources required for investigation are not fully onboarded to SIEM | DE.CM-1 / DE.DP-1 | A.8.15 (Logging), A.8.16 (Monitoring activities) | IV.1 | 2 | SIEM integration map incomplete; missing DNS/Proxy/VPN logs in some environments | Missing critical telemetry causes investigation blind spots | Incomplete timeline and RCA; increased dwell time | P1 | EDR telemetry and firewall logs only | Prioritize onboarding: DNS, Proxy, VPN, AD, Cloud audit logs; update SIEM Integration Map | SOC Engineer / SIEM Owner | Network, IAM, Cloud teams | YYYY-MM-DD | Open | SIEM integration checklist; log onboarding evidence; ingestion health logs | YYYY-MM-DD | MSSP: validate per client onboarding scope
GAP-004 | Log Retention | Retention duration & immutability | Logs must be retained long enough for investigations/audit and protected from tampering | DE.DP-4 / PR.DS-6 | A.8.15 (Logging) | IV.1 | 2 | SIEM retention 30 days hot; archive not consistent for all sources | Log retention may be insufficient for late discovery incidents | Investigation cannot cover full kill chain; audit nonconformity | P2 | Manual export of critical logs per incident | Define retention standard (e.g., 180/365 days) and immutable archive for critical logs | IT Ops + SIEM Owner | Storage team, Budget approval | YYYY-MM-DD | Open | Retention policy, storage configs, sample retrieval test evidence | YYYY-MM-DD | Align with RBI / contractual requirements
GAP-005 | Time Synchronization | NTP / time drift | Time sync required across systems for accurate incident timelines | DE.AE-1 / RS.AN-1 | A.8.15 (Logging) | IV.1 | 2 | Some endpoints show time drift in logs | Inaccurate timestamps affect correlation and forensics | Misleading timelines; incorrect attribution; response delays | P2 | SIEM correlation tolerances; manual adjustments | Enforce NTP across servers/endpoints; monitor drift; alert on >120 sec drift | IT Ops | AD/Infra teams | YYYY-MM-DD | In Progress | NTP compliance report; drift alerts; change tickets | YYYY-MM-DD | Include cloud time sync validation
GAP-006 | Incident Classification | Consistency of severity assignment | Severity classification must be consistent across teams/clients | RS.RP-1 / RS.AN-1 | A.5.25 (Assessment and decision on information security events) | V.1 | 3 | Severity matrix exists but reclassification notes missing in tickets | Severity sometimes inconsistent due to missing business impact inputs | SLA breaches; wrong escalation; client dissatisfaction | P2 | SOC Lead review for P1/P2 | Add mandatory ticket fields: business impact, scope, data type; enforce SOC Lead approval for severity changes | SOC Lead | Ticketing admin | YYYY-MM-DD | Open | Ticket QA report; sample tickets with complete classification fields | YYYY-MM-DD | MSSP: ensure client impact confirmation captured
GAP-007 | Playbooks | Playbook version control and review | Playbooks must be maintained, reviewed, and updated post-incident | RS.RP-1 / RS.IM-1 | A.5.24 (Incident management planning), A.5.27 (Learning from incidents) | V.1 / V.6 | 3 | Playbooks exist but review dates not consistently updated | Playbook drift and outdated steps after tool changes | Ineffective response; audit findings | P3 | Ad-hoc updates by L3/SOC Lead | Create quarterly playbook review cadence; add change log; align to tool updates | SOC Manager | Tool owners, IR Team | YYYY-MM-DD | In Progress | Playbook update log; review sign-offs; PIR action linkage | YYYY-MM-DD | Track changes in Playbook-Update-Log
GAP-008 | Evidence Handling | Chain-of-custody consistency | CoC required for legal/regulatory defensibility | RS.AN-3 | A.5.28 (Collection of evidence) | V.3 | 2 | CoC templates exist but not used for all P1/P2 cases | Incomplete evidence traceability | Legal risk; regulator challenges; weak prosecution/disciplinary action | P1 | Evidence stored in secured folder with limited access | Make CoC mandatory for P1/P2; implement evidence checklist; quarterly audit of evidence packages | IR Team Lead | IR training, Storage controls | YYYY-MM-DD | Open | Completed CoC forms; evidence log with hashes; storage access audit logs | YYYY-MM-DD | MSSP: define evidence transfer rules per client
GAP-009 | Regulatory Reporting | Readiness and testing | Regulatory reporting timelines must be met; process must be tested | RS.CO-2 / ID.GV-3 | A.5.5 (Contact with authorities) | I.5 / VI.3 | 3 | Templates exist; no recent reporting drill conducted | Process not rehearsed; risk missing RBI/CERT-In deadlines | Regulatory penalties; reputational damage | P1 | Compliance team on-call | Run annual reporting drill; maintain authority contacts; define timeline checklist per regulator | Compliance / GRC | SOC Lead, Legal | YYYY-MM-DD | Open | Drill report; updated contact list; sample submission package | YYYY-MM-DD | Keep separate client vs internal reporting logic
GAP-010 | Communications | Single source of truth during P1/P2 | Bridge call + ticket must maintain authoritative timeline and actions | RS.CO-3 / RS.CO-2 | A.5.26 (Response to incidents) | V.2 | 3 | Tickets updated but bridge notes not consistently attached | Inconsistent updates cause confusion and delays | Mistakes; duplicated effort; wrong decisions | P2 | SOC Lead manages updates manually | Standardize bridge-call minutes template and attach to ticket every 30/60 mins | SOC Lead | Ticketing workflow | YYYY-MM-DD | In Progress | Sample incident with bridge minutes; comms cadence compliance report | YYYY-MM-DD | Enforce via SOCLead-P1-P2 SOP
GAP-011 | SLA Operations | SLA timer automation and breach alerts | SLA measurement must be reliable and real-time | RS.RP-1 / RS.CO-1 | A.5.24 | V.1 | 2 | SLA timers tracked manually for some workflows | Hard to detect at-risk SLAs early | SLA breaches; client escalations | P2 | Daily manual checks by SOC Lead | Configure ticketing automation: SLA timers, 75% warning alerts, breach alerts; dashboard | SOC Manager / SDM | Ticketing admin | YYYY-MM-DD | Open | SLA dashboard screenshots; automated notifications; breach register entries | YYYY-MM-DD | Map to SLA-Breach-Escalation-Procedure
GAP-012 | Ticket Quality | Standard fields and minimum documentation | Tickets must contain minimum details for audit and handovers | DE.DP-4 / RS.CO-3 | A.5.25 / A.5.26 | V.1 | 3 | Some tickets missing affected assets, timestamps, evidence links | Incomplete incident records | Audit gaps; poor PIR/RCA; weak client reporting | P3 | QA spot checks by SOC Lead | Define required ticket fields; add templates; monthly QA scoring with coaching | SOC Lead | Ticketing platform config | YYYY-MM-DD | In Progress | QA report; completeness score; training records | YYYY-MM-DD | Align with report templates
GAP-013 | Threat Hunting | Hunting cadence and documentation | Proactive hunting should exist and outputs tracked | DE.AE-2 / RS.AN-1 | A.8.16 | IV.4 | 2 | Ad-hoc hunts only; no hunt plan register | Reduced early detection of persistent threats | Increased dwell time | P3 | IOC sweeps during incidents | Create monthly hunt plan; maintain hunt reports; convert findings to detections | L3 / Threat Hunter | SIEM engineer | YYYY-MM-DD | Open | Hunt plan, hunt report, resulting detection rules and tickets | YYYY-MM-DD | Track outputs in Threat-Intel-Output
GAP-014 | Vulnerability Response | Vulnerability-to-incident linkage | Incident RCA should link to vuln/misconfig and track remediation | ID.RA-1 / RS.IM-1 | A.8.8 (Technical vulnerability management) | IV.2 | 2 | RCA sometimes identifies vuln but remediation tracking inconsistent | Remediation actions lost after closure | Recurring incidents; audit issues | P2 | Action tracker exists but not enforced | Force PIR action items for vuln-related incidents; monthly remediation status review | SOC Manager + IT Ops | Vuln Mgmt tool, Change mgmt | YYYY-MM-DD | Open | Action tracker updates; patch proof; risk acceptance if delayed | YYYY-MM-DD | Include SLA for critical patching
GAP-015 | Recovery Validation | Return-to-service (RTS) criteria consistency | RTS decision should be controlled and documented | RC.RP-1 | A.5.26 / A.5.27 | V.5 | 3 | RTS approvals not consistently captured in ticket | RTS may occur before full validation | Reinfection; repeat outage | P2 | IR Team verbal confirmation | Add RTS checklist and mandatory sign-off field; include integrity verification evidence | IR Team Lead | App owners, IT Ops | YYYY-MM-DD | In Progress | RTS checklist, approval record, post-recovery monitoring evidence | YYYY-MM-DD | Align with IRT-Closure-Criteria
GAP-016 | MSSP Multi-Tenant | Data segregation assurance | Evidence and telemetry must be segregated per client | ID.GV-1 / PR.DS-1 | A.5.19 (Supplier relationships) | I.1 / III.8 | 3 | Policy exists but technical verification not documented | Insufficient audit evidence for segregation | Client data leakage risk; contractual breach | P1 | Access restricted by RBAC | Implement quarterly access review; document segregation controls; add audit evidence package | SDM + SOC Manager | Tenant configuration owners | YYYY-MM-DD | Open | Access review records; RBAC screenshots; audit report snippet | YYYY-MM-DD | Critical for MSSP audits
GAP-017 | Contact Directory | Accuracy and availability | Contacts must be current for P1/P2 notification | RS.CO-2 | A.5.5 | V.2 / VI.3 | 2 | Contacts exist but not validated quarterly | Delayed notifications due to outdated contacts | SLA breach; escalation failure | P2 | Secondary contacts sometimes used | Quarterly contact validation drill; update process during onboarding/offboarding | SDM + SOC Lead | Client stakeholders | YYYY-MM-DD | Open | Validation call logs; updated contact list; sign-off email | YYYY-MM-DD | Include after-hours escalation
GAP-018 | Training & Exercises | Minimum exercise frequency | Tabletop/drills must be conducted and documented | PR.IP-9 / RS.IM-1 | A.5.24 / A.5.27 | VI.4 | 2 | TTX scenarios exist but schedule not consistently met | Exercises not completed per plan | Unprepared response; audit findings | P3 | New joiner onboarding only | Publish annual drill calendar; track attendance; produce After Action Reports | SOC Manager + IR Lead | Management scheduling | YYYY-MM-DD | Open | Drill schedule, attendance, AAR, action closure evidence | YYYY-MM-DD | Target: 2 TTX/year minimum
GAP-019 | Detection Engineering | False positive reduction & rule tuning | Tuning required to maintain detection quality | DE.DP-4 / DE.AE-2 | A.8.16 | IV.4 | 3 | FP rate high for some use cases; tuning backlog | Triage overload; missed true positives | Operational fatigue; SLA risk | P2 | QA review and manual filtering | Monthly tuning sprint; prioritize noisy rules; document tuning changes | SIEM Owner + L3 | SOC Lead input | YYYY-MM-DD | In Progress | Tuning log; FP rate trend; updated rules evidence | YYYY-MM-DD | Link tuning to SIEM-Alert-Tuning-Guide
GAP-020 | Placeholder (Add Row) | [6 empty] | 0 |  |  |  | P4 |  |  |  |  | YYYY-MM-DD | Open |  | YYYY-MM-DD
GAP-021 | Placeholder (Add Row) | [6 empty] | 0 |  |  |  | P4 |  |  |  |  | YYYY-MM-DD | Open |  | YYYY-MM-DD