## Sheet1
Sheet Name | Purpose
Instructions | Document usage guide and field definitions
Action Items | Main tracker for all action items
Status Definitions | Status values and meanings
Priority Definitions | Priority values and meanings
Category Definitions | Category values and meanings
Dashboard | Summary metrics (optional pivot)

## Sheet2
Action ID | Source Type | Source Reference | Source Date | Action Title | Action Description | Category | Sub-Category | Priority | Tenant Scope | Affected Client(s) | Owner Role | Owner Name | Secondary Owner | Approver | Status | Status Date | Created Date | Due Date | Extended Due Date | Closed Date | Days Open | SLA Breach (Y/N) | Completion % | Effort Estimate (hours) | Actual Effort (hours) | Dependencies | Blockers | Resources Required | Budget Required | Risk if Not Closed | Closure Evidence Link | Verification By | Verification Date | Verification Status | Lessons Learned ID Link | Playbook Update Log Link | Detection Improvement Link | Control Gap Link | Comments / Notes | Last Updated | Updated By
AI-2026-0001 | TTX | TTX-APT-2026-Q2 AAR | 2026-04-15 | Update APT playbook with new CCIC trigger criteria | During TTX, CCIC activation was delayed by 25 minutes due to unclear trigger criteria for multi-tenant correlation | Playbook Update | Cross-Client Incident Procedure | P2 | MSSP-Wide | N/A (Internal) | IR Team Lead | John Smith | Sarah Johnson | MSSP CISO | In Progress | 2026-04-30 | 2026-04-15 | 2026-05-15 | 2026-05-22 | - | 37 | No | 60 | 16 | 10 | None | None | IR Team Lead time | None | Delayed multi-client response in real APT | - | - | - | - | LL-2026-0042 | PUL-2026-0018 | - | - | Initial draft complete, peer review pending | 2026-04-30 | John Smith
AI-2026-0002 | Incident | INC-2026-0234 (Ransomware) | 2026-03-10 | Create EDR detection rule for BlackTide encryption pattern | Real incident showed EDR did not detect mass file modification pattern fast enough | Detection Improvement | EDR Rule | P1 | MSSP-Wide | BankAlpha | Detection Engineer | Priya Sharma | Rahul Verma | Detection Eng Lead | Closed | 2026-04-05 | 2026-03-10 | 2026-04-01 | - | 2026-04-05 | 26 | No | 100 | 24 | 28 | SIEM data feed | None | Detection Eng time | None | Missed future ransomware encryption events | https://internal/det-rules/BT-ENC-001 | Detection Eng Lead | 2026-04-05 | Verified | LL-2026-0028 | - | DIL-2026-0017 | - | Rule deployed to production, validated in next purple team | 2026-04-05 | Priya Sharma
AI-2026-0003 | Purple Team | PT-2026-Q1 AAR | 2026-02-20 | Add detection for T1003.006 DCSync | Purple team identified no detection for DCSync attacks from non-DC sources | Detection Improvement | SIEM Rule | P1 | MSSP-Wide | N/A (Portfolio) | Detection Engineer | Amit Kumar | - | Detection Eng Lead | In Progress | 2026-04-25 | 2026-02-20 | 2026-03-20 | 2026-04-30 | - | 74 | Yes | 80 | 20 | 35 | Domain Controller log feed validation | Some tenants missing 4662 events | Detection Eng time + per-client log validation | None | APT/credential dumping undetected | - | - | - | - | - | - | DIL-2026-0008 | - | Per-client log coverage issue identified, validating with SDMs | 2026-04-25 | Amit Kumar
AI-2026-0004 | Audit | ISO 27001 Surveillance 2026 | 2026-03-25 | Document evidence retention for cross-client TI sharing | External auditor noted no documented retention for sanitized cross-tenant intel artifacts | Compliance | Documentation | P2 | MSSP-Wide | N/A | Compliance Lead | Meera Reddy | - | MSSP CISO | Closed | 2026-04-20 | 2026-03-25 | 2026-04-25 | - | 2026-04-20 | 26 | No | 100 | 8 | 6 | None | None | Compliance Lead time | None | ISO non-conformity in next audit | https://internal/policies/TI-retention-v1.2 | MSSP CISO | 2026-04-22 | Verified | - | - | - | - | Policy updated, NCR closed | 2026-04-22 | Meera Reddy
AI-2026-0005 | Red Team | RT-2026-Q1 Black Box AAR | 2026-02-28 | Implement detection for lateral movement via WMI | Red team moved laterally via WMI undetected for 4 hours | Detection Improvement | EDR + SIEM Correlation | P1 | MSSP-Wide | N/A (Portfolio) | Detection Engineer | Priya Sharma | - | Detection Eng Lead | In Progress | 2026-04-28 | 2026-02-28 | 2026-04-15 | 2026-05-15 | - | 60 | Yes | 70 | 30 | 25 | Sysmon event 19/20/21 across tenants | Not all tenants have Sysmon | Detection Eng + per-tenant Sysmon deployment | Sysmon deployment cost | WMI lateral movement undetected | - | - | - | - | - | - | DIL-2026-0011 | CGT-2026-0023 | Detection rule ready, Sysmon coverage gap being addressed per-tenant | 2026-04-28 | Priya Sharma
AI-2026-0006 | Lessons Learned | LL-2026-0035 (Insider Threat) | 2026-03-18 | Document HR engagement protocol for insider threat | Insider threat investigation suffered delayed HR engagement due to unclear protocol | Process Update | HR Coordination | P2 | MSSP-Wide | N/A | IR Team Lead | John Smith | - | MSSP CISO | Closed | 2026-04-12 | 2026-03-18 | 2026-04-18 | - | 2026-04-12 | 25 | No | 100 | 12 | 10 | HR Lead review | None | IR Team Lead + HR Lead time | None | Future insider threats face same delay | https://internal/playbooks/insider-HR-protocol-v2 | HR Lead | 2026-04-14 | Verified | LL-2026-0035 | PUL-2026-0014 | - | - | HR-Legal coordination playbook updated | 2026-04-14 | John Smith
AI-2026-0007 | Client Audit | BankAlpha Annual Audit 2026 | 2026-04-01 | Provide per-client SLA breach RCA template | Client requested standard RCA template for SLA breaches | Documentation | Template | P3 | BankAlpha | BankAlpha | SDM Lead | Vikram Singh | - | Compliance Lead | Open | - | 2026-04-01 | 2026-05-01 | - | - | 30 | No | 0 | 6 | 0 | None | None | SDM + Compliance time | None | Client dissatisfaction | - | - | - | - | - | - | - | - | Template draft in progress | 2026-04-15 | Vikram Singh
AI-2026-0008 | BAS Continuous | BAS Weekly Report 2026-W14 | 2026-04-08 | Tune SIEM rule for false positive on legitimate admin PowerShell | BAS triggered FP on legitimate sysadmin activity weekly | Tuning | SIEM Rule Tuning | P3 | MSSP-Wide | N/A | Detection Engineer | Amit Kumar | - | Detection Eng Lead | In Progress | 2026-04-29 | 2026-04-08 | 2026-05-08 | - | - | 22 | No | 40 | 8 | 4 | None | None | Detection Eng time | None | Alert fatigue, missed real events | - | - | - | - | - | - | DIL-2026-0024 | - | Identifying admin baseline patterns | 2026-04-29 | Amit Kumar
AI-2026-0009 | Post-Incident | INC-2026-0156 (Data Breach) | 2026-02-10 | Establish DPO escalation protocol | Data breach incident had unclear DPO engagement timing | Process Update | Regulatory Coordination | P1 | MSSP-Wide | N/A | Compliance Lead | Meera Reddy | Legal Counsel | MSSP CISO | Closed | 2026-03-15 | 2026-02-10 | 2026-03-10 | - | 2026-03-15 | 33 | Yes | 100 | 16 | 14 | Legal review | None | Compliance + Legal time | None | DPDP compliance gap | https://internal/SOPs/DPO-engagement-v1 | MSSP CISO | 2026-03-18 | Verified | LL-2026-0019 | PUL-2026-0008 | - | CGT-2026-0011 | DPO engagement now in IR Team activation criteria | 2026-03-18 | Meera Reddy
AI-2026-0010 | Onboarding | L2 Cohort 2026-Q1 Training Feedback | 2026-03-22 | Add advanced KQL training module to L2 onboarding | New L2 analysts reported gaps in KQL skills for cross-source pivoting | Training | Onboarding Update | P3 | MSSP-Wide | N/A | Training Lead | Anjali Iyer | Detection Eng Lead | SOC Manager | Open | - | 2026-03-22 | 2026-05-22 | - | - | 38 | No | 20 | 24 | 5 | Detection Eng lab access | None | Training Lead + Detection Eng time | None | Continued L2 skills gap | - | - | - | - | - | - | - | - | Module outline drafted | 2026-04-20 | Anjali Iyer

## Sheet3
Status | Definition | Color Code
Open | Action item identified, owner assigned, work not yet started | Red
In Progress | Work actively underway | Yellow
On Hold | Work paused due to dependency or blocker | Orange
Pending Verification | Work complete, awaiting verification by approver | Light Blue
Closed | Verified complete, no further action | Green
Cancelled | Action item no longer applicable | Grey
Reopened | Previously closed item requires additional work | Red

## Sheet4
Priority | Definition | SLA (Default) | Escalation Threshold
P1 - Critical | Severe risk if not closed; regulatory/safety/major operational impact | 30 days | 75% of SLA
P2 - High | Significant risk; material operational/compliance impact | 60 days | 75% of SLA
P3 - Medium | Moderate risk; operational improvement | 90 days | 75% of SLA
P4 - Low | Minor risk; nice-to-have improvement | 180 days | 75% of SLA

## Sheet5
Category | Description | Typical Source
Playbook Update | Changes to incident response playbooks | TTX, Incident, Audit
Detection Improvement | New or tuned detection rules | Purple Team, Red Team, BAS, Incident
Process Update | SOP or procedural changes | Incident, Audit, TTX
Training | Onboarding or skills development | Onboarding feedback, Performance review
Compliance | Regulatory or audit-driven | Audit, Regulatory change
Documentation | New or updated documentation | Audit, Onboarding, Incident
Tooling | Tool deployment, integration, or upgrade | Detection gap, Tool review
Control | Security control implementation | Risk assessment, Audit
Communication | Communication template or channel | Incident, Client feedback
Tuning | Rule or alert tuning | FP analysis, BAS
Infrastructure | IT/SOC infrastructure changes | Capacity review, Incident
Vendor | Vendor coordination or change | Vendor incident, Procurement
Client-Specific | Per-client customization | Client audit, Client request
Other | Does not fit above categories | Various

## Sheet6
Metric | Value | Target | Status
Total Action Items | 10 | - | -
Open | 2 | - | -
In Progress | 4 | - | -
Closed | 4 | - | -
Closure Rate (90 days) | 40% | ≥80% | Below Target
SLA Compliance % | 70% | ≥95% | Below Target
P1 Open | 0 | 0 | On Target
P2 Open | 3 | - | -
P3 Open | 4 | - | -
Items > 60 days open | 3 | - | Review needed
Average days to closure | 30 | ≤45 | On Target