## Index
Sheet Name | Purpose
Instructions | Document usage guide and field definitions
Control Gaps | Main tracker for all identified control gaps
Framework Mapping | Map gaps to NIST CSF, ISO 27001, RBI controls
Gap Severity | Severity level definitions
Gap Status | Status definitions
Control Domains | Control domain definitions
Risk Treatment | Risk treatment options
Dashboard | Summary metrics and trends

## Sheet1
Gap ID | Date Identified | Identification Source | Source Reference | Gap Title | Gap Description | Control Domain | Control Sub-Domain | NIST CSF Function | NIST CSF Category | NIST CSF Subcategory | ISO 27001 Annex A Control | RBI CSF Reference | Other Framework Reference | Current State | Target State | Gap Severity | Likelihood | Impact | Risk Score | Tenant Scope | Affected Client(s) | Affected Systems / Assets | Business Impact if Exploited | Detection in Place (Y/N) | Compensating Controls | Risk Treatment Decision | Treatment Rationale | Remediation Approach | Remediation Owner | Remediation Sponsor | Estimated Effort (hours) | Estimated Budget | Required Resources | Dependencies | Target Closure Date | Extended Closure Date | Actual Closure Date | Status | Last Reviewed Date | Next Review Date | Verification Method | Verification By | Verification Status | Linked Lessons Learned | Linked Action Item | Linked Detection Improvement | Linked Security Improvement | Audit Reference | Regulatory Implication | Comments | Last Updated | Updated By
CGT-2026-0001 | 2026-01-10 | Internal Audit | ISMS-INT-AUDIT-2026-Q1 | No documented MFA bypass detection | Azure AD MFA bypass attempts (T1556) not detected in SIEM | Identity & Access Management | Authentication Monitoring | Detect | DE.CM | DE.CM-01 | A.5.16, A.5.17, A.8.5 | Annex II – Access Control | MITRE T1556 | MFA configured but bypass attempts not alerted | Real-time alerting on MFA bypass attempts | High | Medium | High | High | MSSP-Wide | N/A (Portfolio) | All cloud-tenant Azure AD | Account takeover, privilege escalation undetected | No | Conditional Access policies | Mitigate | Critical detection gap for cloud-first clients | Deploy MFA bypass detection rule in SIEM; integrate Azure AD risk events | Detection Engineer | Detection Eng Lead | 24 | Internal effort only | Azure AD risk events feed | Per-tenant Azure AD log feed | 2026-03-15 | - | 2026-03-12 | Closed | 2026-04-15 | 2026-10-15 | Purple Team Validation | Detection Eng Lead | Verified | LL-2026-0001 | AI-2026-0011 | DIL-2026-0003 | SIR-2026-0008 | ISMS-INT-AUDIT-2026-Q1 | ISO 27001 A.5.17 compliance | Validated in Q2 purple team | 2026-04-15 | Priya Sharma
CGT-2026-0002 | 2026-01-15 | Risk Assessment | Annual Risk Assessment 2026 | Inconsistent log retention across tenants | Some tenants retain logs | Logging & Monitoring | Log Retention | Identify | ID.AM | ID.AM-03 | A.8.15 | Annex II – Logging | CERT-In Direction 28/2022 | Per-tenant retention varies 30-365 days | All tenants minimum 180-day retention | Critical | High | High | Critical | MSSP-Wide | 5 tenants below threshold | SIEM log indexes | CERT-In non-compliance | Yes | Documentation only | Mitigate | Regulatory non-compliance risk | Per-tenant retention review + extension; client coordination for cost | IT Lead | MSSP CISO | 60 | Storage cost per tenant | Storage capacity, client approvals | Client budget approvals | 2026-04-30 | 2026-06-30 | - | In Progress | 2026-04-25 | 2026-05-25 | Tenant retention audit | Compliance Lead | Pending | - | AI-2026-0021 | - | SIR-2026-0014 | Annual Risk Assessment | CERT-In 180-day mandate | 3 of 5 tenants extended, 2 pending budget approval | 2026-04-25 | Compliance Lead
CGT-2026-0003 | 2026-02-05 | Red Team Exercise | RT-2026-Q1 Black Box | No detection for WMI lateral movement | WMI lateral movement (T1021.006) undetected in red team exercise for 4 hours | Detection & Response | Lateral Movement Detection | Detect | DE.AE | DE.AE-02 | A.8.16 | Annex II – SOC Monitoring | MITRE T1021.006 | No detection rule for WMI lateral movement | Real-time WMI lateral movement detection | Critical | High | High | Critical | MSSP-Wide | N/A (Portfolio) | All endpoints | Undetected lateral movement during attacks | No | None | Mitigate | Major detection gap | Deploy WMI detection rule + per-tenant Sysmon deployment | Detection Engineer | Detection Eng Lead | 40 | Sysmon deployment cost | Sysmon coverage across tenants | Per-tenant Sysmon rollout | 2026-04-15 | 2026-05-15 | - | In Progress | 2026-04-28 | 2026-05-28 | Purple Team Validation | Detection Eng Lead | Pending | LL-2026-0006 | AI-2026-0005 | DIL-2026-0011 | SIR-2026-0011 | RT-2026-Q1 AAR | None direct | Sysmon deployment 60% complete | 2026-04-28 | Priya Sharma
CGT-2026-0004 | 2026-02-12 | Incident | INC-2026-0156 (Data Breach) | No DPO engagement protocol in IR activation | DPO engaged 8 hours late during data breach; no formal protocol | Incident Response | Regulatory Coordination | Respond | RS.CO | RS.CO-04 | A.5.24, A.5.34 | Annex II – Incident Management | DPDP Act Section 8 | Ad-hoc DPO engagement | DPO engaged within 1 hour of breach declaration per documented protocol | High | Medium | High | High | MSSP-Wide | N/A | All tenants with PII | DPDP non-compliance, delayed notification | No | Manual escalation | Mitigate | Regulatory and legal exposure | Add DPO to IR Team activation criteria with 1-hour SLA; per-client DPO contacts | Compliance Lead | MSSP CISO | 16 | Internal | Per-client DPO contact list | None | 2026-03-15 | - | 2026-03-12 | Closed | 2026-04-12 | 2026-10-12 | Procedure validation | MSSP CISO | Verified | LL-2026-0005 | AI-2026-0009 | - | - | INC-2026-0156 | DPDP Section 8 | Now in IRT activation criteria | 2026-04-12 | Meera Reddy
CGT-2026-0005 | 2026-02-20 | ISO 27001 Audit | ISO Surveillance Audit 2026 | Cross-tenant TI sharing retention undocumented | Sanitized cross-tenant TI artifacts have no documented retention period | Threat Intelligence | TI Lifecycle Management | Identify | ID.RA | ID.RA-03 | A.5.7, A.5.33 | Annex II – Threat Intelligence | - | No documented retention | Documented retention per TLP and source | Medium | Low | Medium | Medium | MSSP-Wide | N/A | TI platform artifacts | ISO non-conformity | Yes | Operational practice | Mitigate | Audit NCR | Document retention policy; integrate into TI SOP | Compliance Lead | MSSP CISO | 8 | Internal | None | None | 2026-04-25 | - | 2026-04-22 | Closed | 2026-04-22 | 2026-10-22 | Document review | MSSP CISO | Verified | LL-2026-0007 | AI-2026-0004 | - | - | ISO Surveillance 2026 | ISO A.5.7 | NCR closed | 2026-04-22 | Meera Reddy
CGT-2026-0006 | 2026-03-05 | Purple Team | PT-2026-Q1 | DCSync attacks undetected across portfolio | No detection for T1003.006 DCSync from non-DC sources | Detection & Response | Credential Theft Detection | Detect | DE.CM | DE.CM-07 | A.8.16 | Annex II – SOC Monitoring | MITRE T1003.006 | No DCSync detection | Real-time DCSync detection portfolio-wide | Critical | Medium | Critical | Critical | MSSP-Wide | N/A (Portfolio) | All Active Directory environments | Undetected credential dumping during APT | No | None | Mitigate | Critical credential theft gap | Deploy DCSync detection rule + validate 4662 event collection per tenant | Detection Engineer | Detection Eng Lead | 35 | Per-tenant log validation | Domain Controller log feed | Per-tenant DC log enablement | 2026-04-30 | 2026-05-30 | - | In Progress | 2026-04-25 | 2026-05-25 | Purple Team Validation | Detection Eng Lead | Pending | LL-2026-0004 | AI-2026-0003 | DIL-2026-0008 | SIR-2026-0009 | PT-2026-Q1 AAR | None direct | Per-tenant 4662 collection validation 70% complete | 2026-04-25 | Amit Kumar
CGT-2026-0007 | 2026-03-15 | Vendor Risk Assessment | Annual Vendor Review | No supply chain compromise detection | No detection for trojanized vendor software updates (T1195.002) | Supply Chain Security | Vendor Monitoring | Identify | ID.SC | ID.SC-04 | A.5.21, A.5.22 | Annex II – Vendor Risk | MITRE T1195.002 | Vendor advisories monitored manually | Automated vendor advisory + post-install behavior detection | High | Low | Critical | High | MSSP-Wide | N/A (Portfolio) | All software with vendor updates | Supply chain compromise undetected | No | Manual vendor advisory tracking | Mitigate | Major risk per SolarWinds-class threats | Vendor advisory feed automation + post-install behavior baselining | Detection Engineer | Threat Intel Lead | 60 | Vendor TI feed subscription | TI platform integration | None | 2026-06-30 | - | - | In Progress | 2026-04-30 | 2026-05-30 | Detection deployment | Detection Eng Lead | Pending | - | - | DIL-2026-0019 | SIR-2026-0018 | Annual Vendor Review | None direct | Vendor TI feed integration in progress | 2026-04-30 | Priya Sharma
CGT-2026-0008 | 2026-03-25 | Incident | INC-2026-0234 (Ransomware) | Backup integrity not regularly tested | Backups corrupted from 7 days prior discovered only during DR activation | Business Continuity | Backup Integrity | Recover | RC.RP | RC.RP-04 | A.5.29, A.5.30, A.8.13 | Annex III – BCP/DR | - | Backups taken but not integrity-tested | Weekly automated backup integrity testing | Critical | High | Critical | Critical | MSSP-Wide | N/A (Portfolio) | All tenant backups | Unrecoverable data loss during DR | No | Offsite backups | Mitigate | Near-miss for unrecoverable data loss | Implement weekly automated backup integrity testing per tenant | IR Team Lead | IT Lead | 80 | Automation tooling | Backup integrity testing tool | Per-tenant backup access | 2026-06-30 | - | - | In Progress | 2026-04-25 | 2026-05-25 | Successful restore test | IT Lead | Pending | LL-2026-0008 | - | - | SIR-2026-0021 | INC-2026-0234 | None direct | Tooling selected; rollout planning | 2026-04-25 | IT Lead
CGT-2026-0009 | 2026-04-05 | Cloud Security Review | Cloud Posture Assessment 2026 | No CSPM continuous monitoring | Cloud security posture only assessed quarterly; misconfigurations not detected real-time | Cloud Security | Cloud Posture Management | Detect | DE.CM | DE.CM-01 | A.5.23, A.8.16 | Annex II – Cloud Security | - | Quarterly cloud posture review | Continuous CSPM monitoring portfolio-wide | High | High | High | Critical | MSSP-Wide | N/A (Portfolio cloud tenants) | All cloud accounts (AWS, Azure, GCP) | Misconfigurations like INC-2026-0289 (S3 public) | No | Quarterly review | Mitigate | Active exposure window risk | Deploy CSPM tool for portfolio cloud tenants | Cloud Specialist | IT Lead | 120 | CSPM licensing | CSPM tool selection | Per-tenant cloud account integration | 2026-09-30 | - | - | Open | 2026-04-30 | 2026-06-30 | CSPM coverage validation | IT Lead | Pending | LL-2026-0012 | - | - | SIR-2026-0024 | Cloud Posture Assessment | None direct | CSPM tool evaluation in progress | 2026-04-30 | IT Lead
CGT-2026-0010 | 2026-04-15 | Client Audit | BankAlpha Annual Audit | No formal cross-tenant correlation audit trail | BankAlpha auditor asked for evidence of audit trail when cross-tenant correlation runs | Threat Intelligence | Cross-Tenant Operations Audit | Protect | PR.AA | PR.AA-04 | A.5.7, A.8.15 | Annex II – Multi-Tenant | - | Operational practice exists; not audit-logged | All cross-tenant correlations logged with attribution | Medium | Low | Medium | Medium | MSSP-Wide | N/A | TI Platform | Client audit non-compliance, multi-tenant risk | Yes (operational) | Manual logging | Mitigate | Client trust + multi-tenant policy compliance | Add audit logging to cross-tenant correlation tooling | Detection Engineer | TI Lead | 24 | Internal | TI platform audit capability | None | 2026-06-15 | - | - | In Progress | 2026-04-28 | 2026-05-28 | Audit log review | TI Lead | Pending | - | - | - | SIR-2026-0026 | BankAlpha Audit 2026 | Multi-tenant policy | Tooling enhancement scoped | 2026-04-28 | Priya Sharma
CGT-2026-0011 | 2026-04-22 | Penetration Test | Annual Pen Test 2026 | Insider threat program no formal monitoring | UEBA deployed but no formal insider threat indicator program | Insider Threat | Behavioral Monitoring | Detect | DE.CM | DE.CM-08 | A.6.4, A.8.16 | Annex II – Insider Threat | MITRE PRE.T1591 | UEBA deployed; reactive only | Proactive insider threat indicator program | Medium | Medium | High | High | MSSP-Wide | N/A (Portfolio) | All employee endpoints | Insider threats undetected proactively | Partial | UEBA | Mitigate | Insider threat is high-impact | Document insider threat indicator program; integrate UEBA + DLP + HR data | IR Team Lead | HR Lead | 48 | UEBA enhancement + HR data integration | Cross-functional HR + IR + UEBA | HR data sharing approval | 2026-08-31 | - | - | Open | 2026-04-30 | 2026-06-30 | Tabletop validation | IR Team Lead | Pending | LL-2026-0003 | - | - | SIR-2026-0028 | Pen Test 2026 | None direct | Cross-functional planning in progress | 2026-04-30 | HR Lead
CGT-2026-0012 | 2026-04-28 | Threat Landscape Review | Quarterly Threat Brief Q2 2026 | No detection for OAuth consent phishing | OAuth consent phishing (T1528) targeting cloud clients; no detection | Identity & Access Management | OAuth Application Monitoring | Detect | DE.CM | DE.CM-07 | A.5.16, A.5.17 | Annex II – Identity Security | MITRE T1528 | No OAuth consent monitoring | OAuth consent phishing detection portfolio-wide | High | Medium | High | High | MSSP-Wide | N/A (Portfolio cloud tenants) | All cloud identity tenants | OAuth account compromise undetected | No | Conditional Access only | Mitigate | Rising attack vector for cloud-first clients | Deploy OAuth consent monitoring rules + Azure AD app governance | Detection Engineer | Detection Eng Lead | 30 | Internal | Azure AD app governance feature | Per-tenant Azure AD config | 2026-07-15 | - | - | Open | 2026-04-30 | 2026-05-30 | Purple Team Validation | Detection Eng Lead | Pending | - | - | - | SIR-2026-0031 | Threat Landscape Brief Q2 | None direct | Detection rule design in progress | 2026-04-30 | Priya Sharma

## Sheet2
Gap ID | NIST CSF Function | NIST CSF Category Code | NIST CSF Category Name | NIST CSF Subcategory | ISO 27001:2022 Annex A | RBI CSF Annex | RBI CSF Control | CIS Controls v8 | PCI DSS (if applicable) | HIPAA (if applicable) | SOC 2 TSC | Mapping Confidence
CGT-2026-0001 | Detect | DE.CM | Security Continuous Monitoring | DE.CM-01 | A.5.16, A.5.17, A.8.5 | Annex II | Access Control | CIS 6.5 | - | - | CC6.1 | High
CGT-2026-0002 | Identify | ID.AM | Asset Management | ID.AM-03 | A.8.15 | Annex II | Logging | CIS 8.1 | Req 10 | 164.312(b) | CC7.2 | High
CGT-2026-0003 | Detect | DE.AE | Anomalies and Events | DE.AE-02 | A.8.16 | Annex II | SOC Monitoring | CIS 13.6 | Req 10 | - | CC7.2 | High
CGT-2026-0004 | Respond | RS.CO | Communications | RS.CO-04 | A.5.24, A.5.34 | Annex II | Incident Management | CIS 17.7 | - | 164.308(a)(6) | CC7.3 | High
CGT-2026-0005 | Identify | ID.RA | Risk Assessment | ID.RA-03 | A.5.7, A.5.33 | Annex II | Threat Intelligence | CIS 18.1 | - | - | CC2.1 | Medium
CGT-2026-0006 | Detect | DE.CM | Security Continuous Monitoring | DE.CM-07 | A.8.16 | Annex II | SOC Monitoring | CIS 13.1 | - | - | CC7.2 | High
CGT-2026-0007 | Identify | ID.SC | Supply Chain Risk Management | ID.SC-04 | A.5.21, A.5.22 | Annex II | Vendor Risk | CIS 15.4 | - | - | CC3.1 | High
CGT-2026-0008 | Recover | RC.RP | Recovery Planning | RC.RP-04 | A.5.29, A.5.30, A.8.13 | Annex III | BCP/DR | CIS 11.3 | Req 9 | 164.308(a)(7) | A1.2 | High
CGT-2026-0009 | Detect | DE.CM | Security Continuous Monitoring | DE.CM-01 | A.5.23, A.8.16 | Annex II | Cloud Security | CIS 12.7 | - | - | CC7.2 | High
CGT-2026-0010 | Protect | PR.AA | Identity Management | PR.AA-04 | A.5.7, A.8.15 | Annex II | Multi-Tenant | CIS 5.1 | - | - | CC6.3 | Medium
CGT-2026-0011 | Detect | DE.CM | Security Continuous Monitoring | DE.CM-08 | A.6.4, A.8.16 | Annex II | Insider Threat | CIS 14.6 | - | 164.308(a)(3) | CC7.2 | Medium
CGT-2026-0012 | Detect | DE.CM | Security Continuous Monitoring | DE.CM-07 | A.5.16, A.5.17 | Annex II | Identity Security | CIS 6.6 | - | - | CC6.1 | High

## Sheet3
Severity | Risk Score | Definition | Examples | Default SLA
Critical | 16-25 | Severe risk of significant breach, regulatory violation, or operational impact | Missing detection for major attack vector; regulatory non-compliance | 30 days
High | 2026-10-15 | Significant risk of breach or compliance issue | Detection gap for common technique; process gap with regulatory implication | 60 days
Medium | 2026-05-09 | Moderate risk of operational or compliance impact | Documentation gap; non-critical control weakness | 90 days
Low | 2026-01-04 | Minor risk, improvement opportunity | Nice-to-have control enhancement; minor process improvement | 180 days
Status | Definition | Next Step
Open | Gap identified, owner assigned, treatment not started | Begin remediation planning
In Progress | Remediation actively underway | Execute remediation plan
Pending Verification | Remediation complete, awaiting verification | Verification testing
Closed | Verified remediation complete | Periodic re-validation
Accepted (Risk) | Risk formally accepted, no remediation planned | Annual review
Transferred | Risk transferred (insurance, vendor, client) | Document transfer mechanism
Deferred | Remediation deferred to future period | Reassess at deferral end
Reopened | Previously closed gap re-identified | Re-remediate

## Sheet4
Control Domain | Description | NIST CSF Alignment | ISO 27001 Alignment
Identity & Access Management | Authentication, authorization, account management | PR.AA, DE.CM | A.5.15-A.5.18, A.8.2-A.8.5
Detection & Response | SOC monitoring, detection, alerting, response | DE.CM, DE.AE, RS | A.5.24-A.5.27, A.8.16
Logging & Monitoring | Log collection, retention, analysis | DE.CM, ID.AM | A.8.15, A.8.16
Threat Intelligence | Threat intel collection, sharing, application | ID.RA, PR.IP | A.5.7
Vulnerability Management | Vulnerability scanning, patching, remediation | ID.RA, PR.IP | A.8.8
Configuration Management | Baselines, hardening, drift detection | PR.IP, DE.CM | A.8.9
Cloud Security | Cloud posture, identity, workload, data | All functions | A.5.23
Endpoint Security | EDR, AV, hardening, monitoring | PR.IP, DE.CM | A.8.1, A.8.7
Network Security | Segmentation, NDR, perimeter | PR.AC, DE.CM | A.8.20-A.8.22
Data Protection | Classification, encryption, DLP | PR.DS | A.5.12, A.8.10-A.8.12
Application Security | WAF, SDLC, app monitoring | PR.IP, DE.CM | A.8.25-A.8.34
Email Security | Gateway, anti-phishing, BEC | PR.IP, DE.CM | A.8.16, A.8.23
Supply Chain Security | Vendor risk, software supply chain | ID.SC | A.5.19-A.5.22
Insider Threat | UEBA, behavioral monitoring | DE.CM | A.6.4, A.8.16
Incident Response | IR planning, playbooks, exercises | RS, RC | A.5.24-A.5.27
Business Continuity | BCP, DR, backup | RC | A.5.29-A.5.30, A.8.13
Physical Security | Facility access, environmental | PR.AC, PR.IP | A.7 (all)
Personnel Security | Background checks, training, NDAs | PR.AT | A.6 (all)
Compliance & Audit | Regulatory, audit readiness | GV (CSF 2.0) | A.5.31, A.5.35, A.5.36
Governance | Policies, RACI, oversight | GV (CSF 2.0) | A.5.1-A.5.6
Cryptography | Key management, encryption standards | PR.DS | A.8.24
Privacy | PII protection, DPDP compliance | PR.DS, RS.CO | A.5.34
Multi-Tenant Operations | Tenant segregation, cross-tenant controls | PR.AC, PR.DS | A.5.10, A.5.12, A.8.3

## Sheet5
Treatment Option | Definition | When to Use | Requires Documentation
Mitigate (Reduce) | Implement controls to reduce risk likelihood or impact | Most gaps; cost-benefit favorable | Remediation plan
Accept | Formally accept risk without remediation | Cost > benefit; risk within tolerance | Risk acceptance form + CISO approval
Transfer | Shift risk to third party | Insurance, vendor SLA, client contractual | Transfer documentation
Avoid | Eliminate the activity creating the risk | Activity not essential; risk too high | Decision documentation
Deferred | Delay remediation to future period | Resource or dependency constraint | Deferral justification + revised date

## Sheet6
Metric | Value | Target | Status
Total Control Gaps Identified (YTD) | 12 | - | -
Critical | 5 | 0 | Above Target
High | 4 | - | -
Medium | 2 | - | -
Low | 1 | - | -
Open Gaps | 8 | - | -
In Progress | 5 | - | -
Closed Gaps | 4 | - | -
Closure Rate (60 days) | 33% | ≥70% | Below Target
Average Days to Closure | 45 | ≤60 | On Target
Critical Open >30 days | 2 | 0 | Action Required
By Domain - Detection & Response | 3 | - | -
By Domain - Identity & Access Management | 2 | - | -
By Domain - Logging & Monitoring | 1 | - | -
By Domain - Cloud Security | 1 | - | -
By Domain - Business Continuity | 1 | - | -
By Domain - Supply Chain Security | 1 | - | -
By Domain - Incident Response | 1 | - | -
By Domain - Threat Intelligence | 1 | - | -
By Domain - Insider Threat | 1 | - | -
NIST Detect Function Gaps | 6 | - | Focus area
NIST Respond Function Gaps | 1 | - | -
NIST Identify Function Gaps | 3 | - | -
NIST Protect Function Gaps | 1 | - | -
NIST Recover Function Gaps | 1 | - | -
ISO 27001 Annex A Affected Controls | 14 | - | -
Risk Accepted Gaps | 0 | - | -
Risk Transferred Gaps | 0 | - | -
Deferred Gaps | 0 | - | -