## Index
Sheet Name | Purpose
Instructions | Document usage guide and field definitions
Security Improvements | Master register of all security improvement initiatives
Improvement Categories | Category definitions
Improvement Status | Status definitions
Source Types | Source type definitions
Priority Definitions | Priority and prioritization framework
Maturity Tracking | Maturity progression per domain
Investment Summary | Budget and resource summary
Dashboard | Summary metrics and trends

## Sheet1
Improvement ID | Date Identified | Source Type | Source Reference | Improvement Title | Improvement Description | Business Justification | Category | Sub-Category | NIST CSF Function | NIST CSF Category | ISO 27001 Annex A | RBI CSF Reference | Maturity Domain | Current Maturity Level | Target Maturity Level | Priority | Tenant Scope | Affected Client(s) | Affected Systems | Owner Role | Owner Name | Sponsor | Stakeholders | Estimated Effort (hours) | Estimated Budget (USD) | Approved Budget (USD) | Actual Spend (USD) | Investment Type | ROI Justification | Required Resources | Dependencies | Risks | Mitigation Plan | Start Date | Target Completion Date | Extended Completion Date | Actual Completion Date | Days Open | Status | Status Date | Phase | Completion % | Milestones Completed | Total Milestones | Verification Method | Verification Owner | Verification Status | Linked Control Gap | Linked Lessons Learned | Linked Action Item | Linked Detection Improvement | Linked Playbook Update | Strategic Initiative | Multi-Year Program | Year 1 Spend | Year 2 Spend | Year 3 Spend | Benefits Realized | Comments | Last Updated | Updated By
SIR-2026-0001 | 2026-01-08 | Strategic Roadmap | 2026 Security Roadmap | Deploy CSPM portfolio-wide | Implement Cloud Security Posture Management for all cloud-using tenants | Continuous cloud misconfiguration detection; eliminate 4-week exposure windows like INC-2026-0289 | Cloud Security | CSPM Deployment | Detect | DE.CM | A.5.23, A.8.16 | Annex II – Cloud | Cloud Security | Level 2 (Periodic) | Level 4 (Continuous Monitoring) | P1 | MSSP-Wide | All cloud tenants | AWS, Azure, GCP | IT Lead | Arjun Mehta | MSSP CISO | Cloud Specialists, SDMs, Detection Eng | 300 | 120000 | 120000 | 35000 | Strategic | Eliminate $500K+ potential breach exposure per misconfiguration | CSPM licensing, integration effort | Per-tenant cloud account integration | Tool selection delay; per-tenant onboarding capacity | Phased rollout; vendor proof-of-concept first | 2026-04-01 | 2026-09-30 | - | - | 30 | In Progress | 2026-04-30 | Phase 1 - Tool Selection | 25 | 2 | 8 | CSPM coverage validation per tenant | IT Lead | Pending | CGT-2026-0009 | LL-2026-0012 | - | - | - | Yes | No | 120000 | - | - | Tool selected, POC underway | Phased rollout planned | 2026-04-30 | Arjun Mehta
SIR-2026-0002 | 2026-01-15 | Risk Assessment | Annual Risk Assessment 2026 | Per-tenant log retention extension to 180+ days | Extend SIEM log retention to minimum 180 days for all tenants per CERT-In | CERT-In regulatory compliance; forensic capability for breach investigations | Logging & Monitoring | Log Retention | Identify | ID.AM | A.8.15 | Annex II – Logging | Logging & Monitoring | Level 2 (Variable) | Level 4 (Compliant) | P1 | MSSP-Wide | 5 non-compliant tenants | SIEM log indexes | IT Lead | Rajesh Kumar | MSSP CISO | Compliance, SDMs, IT Storage | 120 | 45000 | 45000 | 15000 | Compliance | Avoid CERT-In regulatory penalties; enable historical breach investigation | Storage expansion, per-tenant cost | Client budget approvals | Client cost objections | Client coordination + value demonstration | 2026-02-01 | 2026-06-30 | - | - | 30 | In Progress | 2026-04-25 | Phase 2 - Tenant Extension | 60 | 3 | 5 | Per-tenant retention audit | Compliance Lead | Pending | CGT-2026-0002 | - | AI-2026-0021 | - | - | No | No | 45000 | - | - | 3 tenants extended, 2 pending | 2 tenants negotiating budget | 2026-04-25 | Rajesh Kumar
SIR-2026-0003 | 2026-01-22 | Strategic Roadmap | 2026 Security Roadmap | 24x7 Threat Hunting Program | Establish dedicated 24x7 proactive threat hunting capability | Move from reactive to proactive detection; reduce mean time to detect (MTTD) | Detection & Response | Threat Hunting | Detect | DE.CM, DE.AE | A.5.7, A.8.16 | Annex II – SOC | Threat Hunting | Level 1 (Ad-Hoc) | Level 3 (Systematic) | P2 | MSSP-Wide | N/A (Portfolio) | SIEM, EDR, NDR, TI | Threat Intel Lead | Kavita Joshi | MSSP CISO | L2, L3, IR Team, Detection Eng | 600 | 180000 | 150000 | 28000 | Strategic | Reduce MTTD by 40%; enable APT detection | 2 additional FTE, advanced training, hunting tooling | Detection Eng support, TI platform | Hiring delays; skill development time | Pre-hire planning; structured training program | 2026-03-01 | 2026-12-31 | - | - | 60 | In Progress | 2026-04-30 | Phase 1 - Hiring | 30 | 2 | 8 | Hunt program metrics | IR Team Lead | Pending | - | - | - | - | - | Yes | Yes | 150000 | 180000 | 200000 | 1 hunter hired, 2nd hiring | First hunts initiated | 2026-04-30 | Kavita Joshi
SIR-2026-0004 | 2026-02-05 | Red Team | RT-2026-Q1 Black Box | WMI lateral movement detection + Sysmon portfolio deployment | Deploy Sysmon across portfolio + WMI lateral movement detection rules | Critical detection gap for portfolio; closes major lateral movement blind spot | Detection & Response | Endpoint Telemetry | Detect | DE.AE | A.8.16 | Annex II – SOC | Detection Engineering | Level 2 (Partial Coverage) | Level 4 (Comprehensive) | P1 | MSSP-Wide | All endpoints | All tenant endpoints | Detection Engineer | Priya Sharma | Detection Eng Lead | IT, SDMs, Cloud teams | 250 | 60000 | 60000 | 22000 | Detection Improvement | Closes detection gap exploited by red team for 4-hour dwell | Sysmon deployment automation, per-tenant capacity | Per-tenant change management approvals | Per-tenant deployment resistance | Phased per-tenant; demonstrate value early | 2026-03-01 | 2026-06-30 | - | - | 60 | In Progress | 2026-04-28 | Phase 2 - Per-Tenant Rollout | 60 | 3 | 5 | Purple team validation | Detection Eng Lead | Pending | CGT-2026-0003 | LL-2026-0006 | AI-2026-0005 | DIL-2026-0011 | - | No | No | 60000 | - | - | 60% of tenants deployed | Q3 completion expected | 2026-04-28 | Priya Sharma
SIR-2026-0005 | 2026-02-15 | Strategic Roadmap | 2026 Security Roadmap | SOAR Maturity Expansion - Phase 2 | Expand SOAR automation to cover 80% of common playbooks (currently 40%) | Reduce analyst toil; improve consistency; faster MTTR | Detection & Response | Automation | Respond | RS.MA | A.8.16 | Annex II – Incident Management | SOAR | Level 2 (Basic) | Level 4 (Advanced) | P2 | MSSP-Wide | N/A | SOAR platform | Detection Eng Lead | Amit Kumar | MSSP CISO | L1/L2/L3, IR Team | 500 | 100000 | 100000 | 18000 | Strategic | Estimated 30% analyst time savings; 25% MTTR reduction | SOAR engineering effort, per-playbook design | Per-client tool integration | Playbook design complexity | Iterative deployment; analyst feedback | 2026-02-15 | 2026-11-30 | - | - | 75 | In Progress | 2026-04-30 | Phase 2 - Playbook Build | 35 | 7 | 20 | Playbook utilization metrics | SOC Manager | Pending | - | - | - | - | - | Yes | Yes | 100000 | 120000 | 100000 | 7 new playbooks live | Adoption tracking positive | 2026-04-30 | Amit Kumar
SIR-2026-0006 | 2026-02-25 | Audit | ISO 27001 Surveillance 2026 | Evidence Management System | Implement centralized evidence repository with retention and lifecycle | Audit-ready evidence at all times; reduce audit preparation time | Compliance & Audit | Evidence Management | Govern | GV (CSF 2.0) | A.5.33, A.5.36 | Annex II – Compliance | Compliance Operations | Level 2 (Manual) | Level 3 (Systematic) | P2 | MSSP-Wide | N/A | Evidence repository, audit records | Compliance Lead | Meera Reddy | MSSP CISO | All control owners | 200 | 50000 | 50000 | 12000 | Compliance | Reduce audit prep effort by 60%; eliminate evidence gaps | Repository tool, taxonomy design | None | Adoption resistance from owners | Training + automation | 2026-03-01 | 2026-08-31 | - | - | 60 | In Progress | 2026-04-22 | Phase 2 - Taxonomy Build | 40 | 2 | 5 | Audit completion test | Compliance Lead | Pending | - | - | - | - | - | No | No | 50000 | - | - | Repository deployed | Taxonomy in progress | 2026-04-22 | Meera Reddy
SIR-2026-0007 | 2026-03-05 | Purple Team | PT-2026-Q1 | DCSync detection + 4662 event collection portfolio-wide | Deploy DCSync detection rules + ensure 4662 event collection on all DCs | Closes critical credential theft detection gap | Detection & Response | Credential Theft Detection | Detect | DE.CM | A.8.16 | Annex II – SOC | Detection Engineering | Level 1 (None) | Level 4 (Comprehensive) | P1 | MSSP-Wide | All AD environments | Domain Controllers | Detection Engineer | Amit Kumar | Detection Eng Lead | IT, SDMs | 150 | 40000 | 40000 | 14000 | Detection Improvement | Closes credential dumping detection gap | Per-tenant DC log configuration | Per-tenant DC log enablement approvals | Some clients lack DC log forwarding | Per-tenant validation + remediation | 2026-03-15 | 2026-06-30 | - | - | 60 | In Progress | 2026-04-25 | Phase 2 - Per-Tenant Validation | 70 | 4 | 6 | Purple team re-validation | Detection Eng Lead | Pending | CGT-2026-0006 | LL-2026-0004 | AI-2026-0003 | DIL-2026-0008 | - | No | No | 40000 | - | - | 70% tenants validated | Q3 completion expected | 2026-04-25 | Amit Kumar
SIR-2026-0008 | 2026-03-15 | Strategic Roadmap | 2026 Security Roadmap | MFA Bypass + Identity Threat Detection | Deploy comprehensive identity threat detection (ITDR) including MFA bypass, OAuth, token theft | Cloud-first identity attacks rising; major gap | Identity & Access Management | ITDR Deployment | Detect | DE.CM, PR.AA | A.5.16, A.5.17 | Annex II – Identity | Identity Security | Level 2 (Basic) | Level 4 (Advanced) | P1 | MSSP-Wide | All cloud identity tenants | Azure AD, Okta, Google Workspace | Detection Engineer | Priya Sharma | Detection Eng Lead | IT, SDMs, Cloud teams | 200 | 75000 | 75000 | 28000 | Strategic | Closes major identity attack vector | ITDR tooling, integration | Per-tenant IdP integration | Tool selection delay | Vendor POC first | 2026-03-15 | 2026-09-30 | - | - | 45 | In Progress | 2026-04-30 | Phase 2 - Deployment | 50 | 3 | 6 | Detection coverage matrix | Detection Eng Lead | Pending | CGT-2026-0001, CGT-2026-0012 | LL-2026-0001 | AI-2026-0011 | DIL-2026-0003 | - | No | No | 75000 | - | - | MFA bypass detection live | OAuth detection in progress | 2026-04-30 | Priya Sharma
SIR-2026-0009 | 2026-03-25 | Incident | INC-2026-0234 (Ransomware) | Backup Integrity Testing Automation | Automated weekly backup integrity testing for all tenants | Prevent unrecoverable data loss; address near-miss from INC-2026-0234 | Business Continuity | Backup Integrity | Recover | RC.RP | A.8.13 | Annex III – BCP/DR | Business Continuity | Level 1 (Manual) | Level 4 (Automated Weekly) | P1 | MSSP-Wide | All tenant backups | Backup infrastructure | IR Team Lead | John Smith | IT Lead | IT, SDMs, BCP team | 250 | 60000 | 60000 | 18000 | Strategic | Prevent multi-million dollar data loss exposure | Automation tooling, per-tenant access | Per-tenant backup access | Tool integration complexity | Phased per-tenant; tested rollout | 2026-04-01 | 2026-08-31 | - | - | 30 | In Progress | 2026-04-25 | Phase 2 - Tool Deployment | 40 | 2 | 5 | Successful integrity test per tenant | IT Lead | Pending | CGT-2026-0008 | LL-2026-0008 | - | - | - | No | No | 60000 | - | - | Tool deployed; per-tenant config in progress | Critical priority | 2026-04-25 | IT Lead
SIR-2026-0010 | 2026-04-05 | Vendor Risk Assessment | Annual Vendor Review | Supply Chain Threat Detection Program | Vendor advisory automation + post-install behavior detection | Major risk per SolarWinds-class threats; portfolio-wide protection | Supply Chain Security | Supply Chain Detection | Identify, Detect | ID.SC, DE.CM | A.5.21, A.5.22 | Annex II – Vendor Risk | Supply Chain Security | Level 1 (Manual) | Level 3 (Automated) | P2 | MSSP-Wide | All vendor software | All tenant endpoints | Threat Intel Lead | Kavita Joshi | MSSP CISO | Detection Eng, IT, Procurement | 350 | 80000 | 80000 | 8000 | Strategic | Detect supply chain compromise like SolarWinds before widespread impact | Vendor TI feed, behavior baseline tooling | TI platform integration | Vendor TI feed coverage limits | Multi-source TI feeds | 2026-04-15 | 2026-10-31 | - | - | 30 | In Progress | 2026-04-30 | Phase 1 - Feed Integration | 20 | 1 | 5 | Vendor advisory + detection metrics | Detection Eng Lead | Pending | CGT-2026-0007 | - | - | DIL-2026-0019 | - | Yes | No | 80000 | - | - | Vendor TI feed integrated | Behavior baseline next | 2026-04-30 | Kavita Joshi
SIR-2026-0011 | 2026-04-15 | Client Audit | BankAlpha Annual Audit | Cross-Tenant Operations Audit Trail | Comprehensive audit logging for all cross-tenant correlation operations | Client trust + multi-tenant policy compliance | Multi-Tenant Operations | Audit Trail | Protect, Govern | PR.AA, GV (CSF 2.0) | A.5.7, A.8.15 | Annex II – Multi-Tenant | Multi-Tenant Operations | Level 2 (Manual) | Level 4 (Automated) | P2 | MSSP-Wide | N/A | TI Platform, SIEM | Detection Engineer | Priya Sharma | TI Lead | Compliance, Multi-Tenant Operations | 120 | 30000 | 30000 | 8000 | Compliance | Client trust; multi-tenant policy compliance evidence | TI platform audit capability | None | Tool capability limits | Tool vendor coordination | 2026-04-22 | 2026-06-30 | - | - | 15 | In Progress | 2026-04-28 | Phase 2 - Implementation | 50 | 2 | 4 | Audit log review | TI Lead | Pending | CGT-2026-0010 | - | - | - | - | No | No | 30000 | - | - | Tool enhancement scoped | Q2 completion expected | 2026-04-28 | Priya Sharma
SIR-2026-0012 | 2026-04-25 | Strategic Roadmap | 2026 Security Roadmap | Insider Threat Program Formalization | Formal insider threat program integrating UEBA + DLP + HR data | Insider threats high-impact; current capability reactive only | Insider Threat | Program Formalization | Detect, Respond | DE.CM, RS.MA | A.6.4, A.8.16 | Annex II – Insider Threat | Insider Threat | Level 2 (Reactive) | Level 4 (Proactive) | P2 | MSSP-Wide | N/A (Portfolio) | UEBA, DLP, HR data | IR Team Lead | John Smith | MSSP CISO | HR, Legal, Detection Eng | 400 | 100000 | 100000 | 5000 | Strategic | Proactive insider threat detection; reduce dwell time | UEBA enhancement, HR data integration | HR data sharing approval, Legal review | Privacy considerations | DPDP-compliant integration design | 2026-05-01 | 2026-11-30 | - | - | 5 | Open | 2026-04-30 | Phase 1 - Program Design | 10 | 1 | 7 | TTX validation | IR Team Lead | Pending | CGT-2026-0011 | LL-2026-0003 | - | - | - | Yes | Yes | 100000 | 120000 | 100000 | Program charter approved | Cross-functional planning underway | 2026-04-30 | John Smith
SIR-2026-0013 | 2026-04-30 | Threat Landscape Review | Quarterly Threat Brief Q2 2026 | OAuth Consent Phishing Detection | Deploy OAuth consent monitoring + Azure AD app governance integration | Rising attack vector for cloud-first clients | Identity & Access Management | OAuth Security | Detect | DE.CM | A.5.16, A.5.17 | Annex II – Identity | Identity Security | Level 1 (None) | Level 4 (Comprehensive) | P1 | MSSP-Wide | All cloud identity tenants | Azure AD | Detection Engineer | Priya Sharma | Detection Eng Lead | IT, SDMs, Cloud teams | 100 | 25000 | 25000 | 2000 | Detection Improvement | Closes rising attack vector | Azure AD app governance, detection rules | Per-tenant Azure AD config | Per-tenant configuration variance | Per-tenant validation | 2026-05-01 | 2026-07-15 | - | - | 0 | Open | 2026-04-30 | Planning | 5 | 0 | 4 | Purple Team Validation | Detection Eng Lead | Pending | CGT-2026-0012 | - | - | - | - | No | No | 25000 | - | - | Detection design in progress | Q3 completion expected | 2026-04-30 | Priya Sharma
SIR-2026-0014 | 2026-04-30 | Strategic Roadmap | 2026 Security Roadmap | Zero Trust Architecture Maturity Roadmap | Multi-year program advancing ZTA maturity across MSSP infrastructure and client offerings | Strategic alignment with industry direction; client expectations | Architecture | Zero Trust | Protect | PR.AA, PR.DS | A.5.15-A.5.18, A.8.3 | Annex II – Identity | Architecture | Level 1 (Traditional) | Level 4 (Advanced ZTA) | P3 | MSSP-Wide | N/A | All infrastructure | IT Architect | Suresh Iyer | MSSP CISO | IT, Detection Eng, Cloud teams | 2000 | 500000 | 100000 | 0 | Strategic | Industry alignment; future client requirement | Architecture redesign, tooling, training | Major infrastructure dependencies | Multi-year complexity; cost | Phased multi-year roadmap | 2026-07-01 | 2028-12-31 | - | - | 0 | Open | 2026-04-30 | Phase 0 - Planning | 5 | 0 | 15 | ZTA maturity assessment | IT Architect | Pending | - | - | - | - | - | Yes | Yes | 100000 | 200000 | 200000 | Roadmap drafted | Board approval pending | 2026-04-30 | Suresh Iyer

## Sheet2
Category | Description | Examples | Typical Investment Range
Detection & Response | SOC detection capability, response automation | New detection rules, SOAR expansion, ITDR | $50K-$200K
Identity & Access Management | IAM, MFA, ITDR, IdP improvements | MFA enforcement, ITDR, OAuth monitoring | $30K-$150K
Cloud Security | CSPM, CWPP, cloud-native security | CSPM deployment, cloud workload protection | $50K-$200K
Logging & Monitoring | Log collection, retention, analysis | SIEM expansion, log retention extension | $25K-$100K
Threat Intelligence | TI feeds, platform, integration | Premium TI feeds, TIP enhancement | $30K-$150K
Vulnerability Management | Vuln scanning, patching automation | Continuous VM, patch automation | $25K-$100K
Endpoint Security | EDR, AV, hardening | EDR rollout, hardening automation | $50K-$200K
Network Security | Segmentation, NDR, perimeter | Network segmentation, NDR deployment | $50K-$300K
Email Security | Gateway, anti-phishing, BEC | Sandbox, BEC detection | $25K-$100K
Data Protection | Classification, encryption, DLP | DLP deployment, encryption upgrade | $50K-$200K
Application Security | WAF, SDLC, app monitoring | WAF, SAST/DAST, app monitoring | $25K-$150K
Supply Chain Security | Vendor risk, SBOM, supply chain detection | Vendor TI feed, SBOM platform | $50K-$200K
Insider Threat | UEBA, DLP, HR integration | UEBA, insider program | $50K-$200K
Incident Response | Playbooks, IR Team, retainers | IR retainer, playbook automation | $30K-$200K
Business Continuity | BCP, DR, backup integrity | Backup automation, DR enhancement | $25K-$150K
Compliance & Audit | Audit readiness, evidence management | Evidence repository, GRC platform | $30K-$150K
Multi-Tenant Operations | Tenant segregation, multi-tenant tooling | Multi-tenant audit, segregation enhancement | $25K-$100K
Automation | SOAR, scripting, workflow automation | SOAR expansion, automation toolkit | $50K-$200K
Architecture | Strategic architecture initiatives | Zero Trust, defense in depth | $100K-$1M+
Training | SOC training programs, certifications | Advanced training, certifications | $25K-$100K
Tooling | Tool deployment, integration, upgrade | Tool consolidation, integration | $25K-$200K
Process | Process maturity, SOPs, governance | Process redesign, governance program | $10K-$100K
Other | Does not fit above | Various | Various

## Sheet3
Category | Description | Examples | Typical Investment Range
Detection & Response | SOC detection capability, response automation | New detection rules, SOAR expansion, ITDR | $50K-$200K
Identity & Access Management | IAM, MFA, ITDR, IdP improvements | MFA enforcement, ITDR, OAuth monitoring | $30K-$150K
Cloud Security | CSPM, CWPP, cloud-native security | CSPM deployment, cloud workload protection | $50K-$200K
Logging & Monitoring | Log collection, retention, analysis | SIEM expansion, log retention extension | $25K-$100K
Threat Intelligence | TI feeds, platform, integration | Premium TI feeds, TIP enhancement | $30K-$150K
Vulnerability Management | Vuln scanning, patching automation | Continuous VM, patch automation | $25K-$100K
Endpoint Security | EDR, AV, hardening | EDR rollout, hardening automation | $50K-$200K
Network Security | Segmentation, NDR, perimeter | Network segmentation, NDR deployment | $50K-$300K
Email Security | Gateway, anti-phishing, BEC | Sandbox, BEC detection | $25K-$100K
Data Protection | Classification, encryption, DLP | DLP deployment, encryption upgrade | $50K-$200K
Application Security | WAF, SDLC, app monitoring | WAF, SAST/DAST, app monitoring | $25K-$150K
Supply Chain Security | Vendor risk, SBOM, supply chain detection | Vendor TI feed, SBOM platform | $50K-$200K
Insider Threat | UEBA, DLP, HR integration | UEBA, insider program | $50K-$200K
Incident Response | Playbooks, IR Team, retainers | IR retainer, playbook automation | $30K-$200K
Business Continuity | BCP, DR, backup integrity | Backup automation, DR enhancement | $25K-$150K
Compliance & Audit | Audit readiness, evidence management | Evidence repository, GRC platform | $30K-$150K
Multi-Tenant Operations | Tenant segregation, multi-tenant tooling | Multi-tenant audit, segregation enhancement | $25K-$100K
Automation | SOAR, scripting, workflow automation | SOAR expansion, automation toolkit | $50K-$200K
Architecture | Strategic architecture initiatives | Zero Trust, defense in depth | $100K-$1M+
Training | SOC training programs, certifications | Advanced training, certifications | $25K-$100K
Tooling | Tool deployment, integration, upgrade | Tool consolidation, integration | $25K-$200K
Process | Process maturity, SOPs, governance | Process redesign, governance program | $10K-$100K
Other | Does not fit above | Various | Various

## Sheet4
Status | Definition | Required Documentation | Next Step
Proposed | Improvement identified, not yet approved | Business case | Approval review
Approved | Approved with budget and owner | Project charter | Begin planning
Open | Approved, planning underway | Project plan | Begin execution
In Progress | Active execution | Status updates | Milestone tracking
On Hold | Paused due to dependency or constraint | Hold reason | Resolve blocker
Pending Verification | Execution complete, verification needed | Verification plan | Verify outcomes
Closed | Complete and verified | Closure report | Lessons learned
Cancelled | No longer pursued | Cancellation rationale | Document and archive
Deferred | Postponed to future period | Deferral rationale and new date | Reassess at deferral end

## Sheet5
Source Type | Description | Typical Trigger
Strategic Roadmap | Annual or multi-year strategic plan | Annual planning
Risk Assessment | Annual or ad-hoc risk assessment | Risk identified
Incident | Real incident lessons learned | Major incident
TTX | Tabletop exercise findings | TTX AAR
Red Team | Red team engagement findings | Red Team AAR
Purple Team | Purple team exercise findings | Purple Team AAR
BAS Continuous | Breach & Attack Simulation findings | BAS report
Internal Audit | Internal ISMS audit findings | Audit report
External Audit | ISO/SOC 2/external audit findings | Audit report
Client Audit | Client right-to-audit findings | Client audit report
Regulatory Inspection | Regulator inspection findings | Regulatory report
Threat Landscape Review | Quarterly threat landscape brief | Threat brief
Vendor Risk Assessment | Vendor security review | Vendor assessment
Penetration Test | Annual pen test findings | Pen test report
Cloud Security Review | Cloud posture assessment | Cloud assessment
Client Request | Specific client requirement | Client request
Competitive Analysis | Market/competitor analysis | Strategy review
Regulatory Change | New regulatory requirement | Regulatory update
Technology Refresh | End-of-life or major upgrade | Lifecycle review
Other | Other sources | Various

## Sheet6
Priority | Definition | Risk-Based Criteria | Strategic Criteria | SLA (Default Target) | Approval Required
P1 - Critical | Highest priority; address immediately | Critical risk if not addressed; regulatory mandate | Critical strategic initiative | 90 days planning + execution per scope | MSSP CISO
P2 - High | High priority; address within current quarter | High risk; significant strategic value | Major strategic initiative | 180 days | MSSP CISO
P3 - Medium | Medium priority; address within current half-year | Medium risk; moderate strategic value | Notable strategic improvement | 365 days | SOC Manager + Compliance Lead
P4 - Low | Low priority; opportunistic | Low risk; nice-to-have | Minor improvement | Multi-year acceptable | SOC Manager

## Sheet7
Maturity Domain | Current Maturity Level | Current Description | Target Maturity Level | Target Description | Active Improvements (IDs) | Maturity Owner | Last Assessment Date | Next Assessment Date | Notes
Detection Engineering | Level 2 (Reactive) | Rules created in response to incidents | Level 4 (Continuous Improvement) | Continuous purple team-driven detection improvement | SIR-2026-0004, SIR-2026-0007, SIR-2026-0008, SIR-2026-0013 | Detection Eng Lead | 2026-01-15 | 2026-07-15 | Active multi-front improvement
Cloud Security | Level 2 (Periodic Assessment) | Quarterly cloud posture review | Level 4 (Continuous CSPM) | Real-time CSPM monitoring | SIR-2026-0001 | IT Lead | 2026-01-15 | 2026-07-15 | CSPM rollout in progress
Identity Security | Level 2 (Basic) | MFA + Conditional Access | Level 4 (Advanced ITDR) | Comprehensive ITDR incl. MFA bypass, OAuth, token theft | SIR-2026-0008, SIR-2026-0013 | Detection Eng Lead | 2026-01-15 | 2026-07-15 | ITDR deployment active
SOAR / Automation | Level 2 (Basic) | 40% playbook automation | Level 4 (Advanced) | 80%+ playbook automation | SIR-2026-0005 | Detection Eng Lead | 2026-01-15 | 2026-07-15 | Phase 2 in progress
Threat Hunting | Level 1 (Ad-Hoc) | Reactive hunting only | Level 3 (Systematic) | 24x7 proactive hunting program | SIR-2026-0003 | Threat Intel Lead | 2026-01-15 | 2026-07-15 | Hiring + program build
Logging & Monitoring | Level 2 (Variable) | Per-tenant retention varies | Level 4 (Compliant) | All tenants 180+ days, audit-ready | SIR-2026-0002 | IT Lead | 2026-01-15 | 2026-07-15 | Per-tenant extension active
Business Continuity | Level 1 (Manual) | Backups taken, integrity not tested | Level 4 (Automated) | Weekly automated integrity testing | SIR-2026-0009 | IR Team Lead | 2026-01-15 | 2026-07-15 | Critical priority
Insider Threat | Level 2 (Reactive) | UEBA reactive only | Level 4 (Proactive) | Comprehensive insider program | SIR-2026-0012 | IR Team Lead | 2026-01-15 | 2026-07-15 | Program design phase
Supply Chain Security | Level 1 (Manual) | Manual vendor advisory tracking | Level 3 (Automated) | Automated vendor advisory + detection | SIR-2026-0010 | Threat Intel Lead | 2026-01-15 | 2026-07-15 | TI feed integrated
Compliance Operations | Level 2 (Manual) | Manual evidence collection | Level 3 (Systematic) | Centralized evidence repository with lifecycle | SIR-2026-0006 | Compliance Lead | 2026-01-15 | 2026-07-15 | Repository deployed
Multi-Tenant Operations | Level 2 (Manual Audit) | Operational logging | Level 4 (Automated Audit) | Comprehensive automated audit trail | SIR-2026-0011 | TI Lead | 2026-01-15 | 2026-07-15 | Tool enhancement underway
Architecture (Zero Trust) | Level 1 (Traditional) | Perimeter-based security | Level 4 (Advanced ZTA) | Comprehensive Zero Trust Architecture | SIR-2026-0014 | IT Architect | 2026-01-15 | 2026-07-15 | Multi-year program

## Sheet8
Category | # Improvements | Total Approved Budget (USD) | YTD Spend (USD) | Remaining Budget (USD) | Spend % | Year 1 Plan | Year 2 Plan | Year 3 Plan | Multi-Year Total | Status
Detection & Response | 3 | 250000 | 78000 | 172000 | 31% | 250000 | 300000 | 100000 | 650000 | On Track
Cloud Security | 1 | 120000 | 35000 | 85000 | 29% | 120000 | 0 | 0 | 120000 | On Track
Logging & Monitoring | 1 | 45000 | 15000 | 30000 | 33% | 45000 | 0 | 0 | 45000 | On Track
Identity & Access Management | 2 | 100000 | 30000 | 70000 | 30% | 100000 | 0 | 0 | 100000 | On Track
Threat Hunting | 1 | 150000 | 28000 | 122000 | 19% | 150000 | 180000 | 200000 | 530000 | On Track
Compliance & Audit | 1 | 50000 | 12000 | 38000 | 24% | 50000 | 0 | 0 | 50000 | On Track
Business Continuity | 1 | 60000 | 18000 | 42000 | 30% | 60000 | 0 | 0 | 60000 | On Track
Supply Chain Security | 1 | 80000 | 8000 | 72000 | 10% | 80000 | 0 | 0 | 80000 | Behind Schedule
Multi-Tenant Operations | 1 | 30000 | 8000 | 22000 | 27% | 30000 | 0 | 0 | 30000 | On Track
Insider Threat | 1 | 100000 | 5000 | 95000 | 5% | 100000 | 120000 | 100000 | 320000 | On Track
Architecture | 1 | 100000 | 0 | 100000 | 0% | 100000 | 200000 | 200000 | 500000 | Planning
TOTAL | 14 | 1085000 | 237000 | 848000 | 22% | 1085000 | 800000 | 600000 | 2485000 | -

## Sheet9
Metric | Value | Target | Status | Trend
Total Improvements Active (YTD) | 14 | - | - | ↑
Proposed | 0 | - | - | -
Open | 2 | - | - | -
In Progress | 11 | - | - | -
Closed | 0 | - | - | -
By Priority - P1 | 7 | - | - | -
By Priority - P2 | 5 | - | - | -
By Priority - P3 | 2 | - | - | -
By Priority - P4 | 0 | - | - | -
Total Approved Budget (USD) | 1085000 | - | - | -
YTD Spend (USD) | 237000 | - | - | -
Budget Utilization % | 22% | On Pace | On Track | -
Multi-Year Program Count | 5 | - | - | ↑
Strategic Initiatives Count | 8 | - | - | ↑
Compliance-Driven Count | 3 | - | - | -
Risk-Driven Count | 6 | - | - | -
Strategic-Driven Count | 5 | - | - | -
Avg Days to Completion (Closed) | - | ≤180 | - | -
Items >180 days In Progress | 0 | 0 | On Target | -
P1 Items Behind Schedule | 1 | 0 | Action Required | -
NIST CSF Improvements - Identify | 3 | - | - | -
NIST CSF Improvements - Protect | 2 | - | - | -
NIST CSF Improvements - Detect | 8 | - | - | Heavy investment
NIST CSF Improvements - Respond | 2 | - | - | -
NIST CSF Improvements - Recover | 1 | - | - | -
NIST CSF Improvements - Govern | 2 | - | - | -
Detection Maturity Level (avg) | 2.4 | 4 | Below Target | ↑
Cloud Security Maturity | 2 | 4 | Below Target | ↑
Identity Security Maturity | 2 | 4 | Below Target | ↑
SOAR Maturity | 2 | 4 | Below Target | ↑
Multi-Tenant Maturity | 2 | 4 | Below Target | ↑
ROI Realized (USD est.) | - | - | - | Tracking begins Q4
Risk Reduction (% est.) | - | - | - | Tracking begins Q4